## Revised Cap Prog 08-02-06
|  | 2005/2006 |  | 2006/2007 | 2007/2008 | 2008/2009 | Prior to
Account | Detail | Original | Revised | Estimate | Estimate | and beyond | 1 April 2005 | Total
Code
|  | £ | £ | £ | £ | £ | £ | £
1. COMMITTED EXPENDITURE
1. CULTURAL, LEISURE & COMMERCIAL SERVICES
98500 | Recycling: Extension to Scheme - Vehicles & Containers | 187350 | 187350 | - | - | - | 1096460 | 1283810
| Recycling: Waste Performance & Efficiency Expenditure | - | - | 40410 | 42320 | - | - | 82730
98020 | Public Conveniences: Enhancement Programme | 27580 | 27580 | - | - | - | 86230 | 113810
| Public Conveniences: Infrastructure and Servicing |  |  | 100000 |  |  |  | 100000
| Rowland Hill Public Conveniences Refurbishment | 40000 | 40000 | - | - | - | - | 40000
98030 | Municipal Cemetery: Purchase of Land | 344290 | 344290 | - | - | - | 5710 | 350000
98035 | Cemetery Main Roadway | 28000 | 28000 | - | - | - | - | 28000
98084 | St Mary's Churchyard Boundary Wall | 25200 | 25200 | - | - | - | 14600 | 39800
98086 | St Mary's Retaining Wall | 49000 | 49000 | - | - | - | - | 49000
| Wyre Forest Glades: Plant Replacement | 342000 | - | 442000 | - | - | 51570 | 493570
| Wyre Forest Glades: Capital Grant towards Refurbishment | 350000 | - | 350000 | - | - | - | 350000
98026 | Glades 'Contingency': Floor Replacement, DDA and Alarms | 80000 | - | 80000 | - | - | - | 80000
98015 | Play Equipment: Replacement/Repairs Programme | 261890 | 261890 | 115000 | - | - | 231110 | 608000
| Play Equipment: Improvements to St Georges Park | - | 30000 | - | - | - | - | 30000
98051 | Paddling Pools: Repairs to Brinton Park & Riverside Pools | 12530 | 12530 | - | - | - | 2470 | 15000
98054 | Skateboard Park at Brinton Park | 60000 | 60000 | - | - | - | - | 60000
| Stourport Footpath (subject to S.106 agreement) | 15300 | - | 15300 | - | - | - | 15300
98053 | Liveability Scheme: Brinton Park | 277860 | 312860 | - | - | - | 25140 | 338000
98052 | Liveability Scheme: QEII Gardens | 76840 | 76840 | - | - | - | 16160 | 93000
98056 | White Wickets Changing Facility | 46000 | - | 66000 | - | - | - | 66000
98088 | Spennells Playing Field: Youth Shelter | 10000 | 10000 | - | - | - | - | 10000
98058 | General Cleansing: Geographic Working | 12600 | 12600 | - | - | - | - | 12600
98057 | Old Pals Shelter: Refurbishment | 43800 | 43800 | 20000 | - | - | - | 63800
| Local Public Service Agreement Scheme: Sport & Recreation | - | - | 69770 | - | - | - | 69770
98040 | Parking Facilities: Payment under Contractual Agreement | 191090 | 191090 | - | - | - | 1410 | 192500
98043 | Parking Facilities: Future Car Parking Contingency | 2000000 | - | 1700000 | - | - | - | 1700000
98042 | Parking Facilities: Remedial/Safety Work to existing Car Parks | 80430 | 80430 | - | - | - | 69570 | 150000 | APPENDIX 4
| Parking Facilities: Improvement to Car Parks | 20000 | 20000 | 100000 | 100000 | 100000 | - | 320000
| Decriminalisation of Parking Enforcement | - | - | 195000 | - | - | - | 195000
| Car Parks Oil Interceptors | 90000 | - | 90000 | - | - | - | 90000
| Vale Road Crossing | 16000 | - | 16000 | - | - | - | 16000
98105 | Administrative Buildings: Imp. Works for Disabled | 170650 | 170650 | - | - | - | 29350 | 200000
| Vicar Street Lease Surrender Contingency | 50000 | 50000 | - | - | - | - | 50000
98085 | Duke House Refurbishment | 18770 | 18770 | - | - | - | 676800 | 695570
|  | 2005/2006 |  | 2006/2007 | 2007/2008 | 2008/2009 | Prior to
| Detail | Original | Revised | Estimate | Estimate | and beyond | 1 April 2005 | Total
|  | £ | £ | £ | £ | £ | £ | £
1. COMMITTED EXPENDITURE (Continued)
1. CULTURAL, LEISURE & COMMERCIAL SERVICES (Cont)
98526 | Worcestershire Hub: Contribution to WCC | 198500 | 198500 | - | - | - | - | 198500
98525 | Worcestershire Hub: Town Hall Conversion | 1235150 | 1359150 | - | - | - | 14850 | 1374000
| Worcestershire Hub: Vicar Street Offices Refurbishment | 125000 | - | 125000 | - | - | - | 125000
98528 | Worcestershire Hub: Civic Centre Reception Remodelling | 30000 | 53000 | - | - | - | - | 53000
98527 | Worcestershire Hub: Bewdley TIC Remodelling | 50000 | 77000 | - | - | - | - | 77000
| Rushock Trading Estate: Repairs & Maintenance | 130000 | 30000 | 100000 | - | - | - | 130000
98087 | KTC 3 Disposal (Costs to be deducted from future Capital Receipt) | 78060 | 78060 | - | - | - | 48180 | 126240
2. PLANNING, HEALTH & ENVIRONMENT
Housing Strategy:
98090 | Disabled Facilities Grants | 800000 | 800000 | 800000 | 800000 | - | 1368320 | 3768320
98550 | Affordable Housing Grants to Registered Social Landlords | 2848420 | 2870600 | 1400000 | 1400000 | 1700000 | 891580 | 8262180
98100 | Private Sector Housing Conditions: Improvements Initiative | 22180 | 100000 | - | - | - | 297600 | 397600
| Community Alarm Equipment Grant | 70000 | 70000 | 70000 | 70000 | 290000 | - | 500000
| Conservation Area: Listed & Heritage Buildings | 10000 | 10000 | 30000 | - | - | - | 40000
| Conservation of the Historic Environment | - | - | - | 30000 | - | - | 30000
98560 | Sustainable Transport: Enhance Pedestrian Access | - | - | 50000 | - | - | - | 50000
| Environmental Improvements - Stourport-on-Severn | - | - | 100000 | - | - | - | 100000
4. HUMAN RESOURCES
99250 | Implementing Electronic Government | 255720 | 255720 | - | - | - | 515780 | 771500
| ICT Investment: Corporate & Benefits Workflow/D.I.P. | 250000 | 50000 | 200000 | - | - | - | 250000
98522 | Software & Network Licenses | 22500 | 22500 | 42900 | 42900 | 20400 | - | 128700
| Software - Sports & Leisure Facilities | - | - | 50000 | - | - | - | 50000
5. STRATEGY & PERFORMANCE UNIT
98115 | CCTV Kidderminster Town Centre | 47300 | 36920 | - | - | - | 82700 | 119620
| CCTV - Stourport-on-Severn & Bewdley (Contingency) | - | - | 170000 | - | - | - | 170000
| Grants to Voluntary Bodies: CAB | 25000 | - | 25000 | - | - | - | 25000
APPENDIX 4
6. LEGAL & DEMOCRATIC SERVICES
98125 | Capital Grant towards Rebuilding Queensway Wall | 45000 | 45000 | - | - | - | - | 45000
| Land Charges: MIS System | 9600 | 9600 | - | - | - | - | 9600
98530 | 7. VEHICLE, EQUIPMENT & SYSTEMS RENEWAL SCHEDULE | 688210 | 688210 | 904000 | 653000 | 450000 | 836300 | 3531510
98535
98540 | TOTAL COMMITTED EXPENDITURE | 11867820 | 8807140 | 7466380 | 3138220 | 2560400 | 6361890 | 28334030
|  | 2005/2006 |  | 2006/2007 | 2007/2008 | 2008/2009
| Detail | Original | Revised | Estimate | Estimate | and beyond
|  | £ | £ | £ | £ | £
2. FINANCING
| Capital Receipts: General | 4961290 | 1581460 | 3527350 | 172900 | 120400
| Capital Receipts: Housing | 3509600 | 3452600 | 2070000 | 2070000 | 1990000
| Disabled Facilities Grant | 231000 | 288000 | 200000 | 200000 | -
| Sale of Land Oak & Coventry Street Premises | 955000 | 1059150 | 19850 | - | -
| KTC 3 Receipt | 78060 | 78060 | - | - | -
| Worcestershire County Council Grant (Hub) | 300000 | 350000 | - | - | -
| Liveability/Heritage Lottery Grant Funding | 354700 | 389700 | - | - | -
| Local Public Service Agreement Scheme Grant: WCC | - | - | 69770 | - | -
| Implementing Electronic Government Grant | 255720 | 255720 | - | - | -
| Implementing Electronic Government Grant (Hub) | 128500 | 128500 | - | - | -
| Grant from DEFRA for Recycling | 187350 | 187350 | - | - | -
| Grant towards Rowland Hill Public Conveniences Refurbishment | 20000 | 20000 | - | - | -
| Waste Performance & Efficiency Grant | - | - | 40410 | 42320 | -
| S.106 Funding (CCTV) | 7300 | 7300 | - | - | -
| S.106 Funding (Parking) | 191090 | 191090 | - | - | -
| S.106 Funding (Cattle Market) | - | 30000 | 20000 | - | -
| S.106 Funding (Sustainable Transport) | - | - | 50000 | - | -
| S.106 Funding (Affordable Housing) | - | 100000 | - | - | -
| Vehicle, Equipment & Systems Renewal (Prudential Borrowing) | 688210 | 688210 | 704000 | 653000 | 450000
| Direct Revenue Funding | - | - | 765000 | - | -
|  | 11867820 | 8807140 | 7466380 | 3138220 | 2560400
NOTE
Original Budget based upon the Amended Capital Programme 2005/2006 approved by Cabinet on 25th August 2005
APPENDIX 4